## SPRINT1
SPRINT 1 (12.5h/person) | 25.04.2023 |  |  | 26.04.2023 |  |  | 27.04.2023 |  |  | 28.04.2023 |  |  | 1.05.2023
TASK | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status

## SPRINT2
SPRINT 2 (12.5h/person) | 2.05.2023 |  |  | 3.05.2023 |  |  | 4.05.2023 |  |  | 5.05.2023 |  |  | 8.05.2023
TASK | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status
Figure out user input requiremnts | Keijo
Make a first paper and pencil scetch of the electronics | Riccardo
Research options for arduino part (handling and displaying the data) | Jari
Write requiremtns for Arduino Code | Jari
Scetch out the case design | Keijo
Make a first raw 3D version of the case design (not print ready - just for reference) | Keijo
Research component options for Arduino | Kadosa

## SPRINT3
SPRINT 3 (12.5h/person) | 9.05.2023 |  |  | 10.05.2023 |  |  | 11.05.2023 |  |  | 12.05.2023 |  |  | 15.05.2023
TASK | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status

## SPRINT4
SPRINT 4 (12.5h/person) | 16.05.2023 |  |  | 17.05.2023 |  |  | 18.05.2023 |  |  | 19.05.2023 |  |  | 22.05.2023
TASK | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status

## SPRINT5
SPRINT 5 (12.5h/person) | 23.05.2023 |  |  | 24.05.2023 |  |  | 25.05.2023 |  |  | 26.05.2023 |  |  | 29.05.2023
TASK | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status

## PROJECT
PROJECT DESCRIPTION
SonicCascadeRhythmRumble is a tool for music produces to help in the creative process and it makes plaing easyer. On the server side we generate key progerssions using AI and send them to a client on the instument to diplsy the cords.
REQUARIMENS
Server hosted code to generate the cords based on some user input from the client using WiFi.
The client uses a simple led based diplay to show the server output and has simple user inputs abilities (i.e. settings knobs).